## Ark1
|  | Planning |  |  |  |  | Design |  |  |  |  | Build |  |  |  |  | Build |  |  |  |  | Launch
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25
Project Manager | Kickoff meeting | Project managment, Customer Contact and Contract |  |  |  | Project managment, Customer Contact and Contract |  |  |  | Kickoff meeting #2 | Project managment, Customer Contact and Contract |  |  |  |  | Project managment, Customer Contact and Contract |  |  |  |  | Project managment, Customer Contact and Contract
Copy Writer | Kickoff meeting | Research |  | Content Planning |  | Text content |  |  |  | Kickoff meeting #2
Photographer | Kickoff meeting |  | Photoshoting Content |  |  | Photoshoting Employees |  |  |  | Kickoff meeting #2
Front-end-developer | Kickoff meeting | Research | [7 empty] | Kickoff meeting #2 | Coding and site build |  |  |  |  | Coding and site build |  |  |  |  | Testing cross plattform and browser |  | Validating |  | Launch
Designer | Kickoff meeting | Research |  | Content Planning |  | Style tiles |  |  |  | Kickoff meeting #2 | [11 empty] | Refinement